## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Milestone 1 | Milestone 1 | US-01 | As a user, I want to submit a question, an AI-generated response, and an optional reference answer, so that the response can be evaluated. | Must | None | Sumeet | Completed
Milestone 1 | Milestone 1 | US-02 | As a system, I want to build a RAG knowledge base from reference datasets so that evaluations are grounded in retrieved context. | Must | US-01 | Sumeet | Completed
Milestone 1 | Milestone 1 | US-03 | As a developer, I want a defined multi-agent architecture, scoring model, and orchestration flow so that the evaluation pipeline has a clear design. | Must | None | Sumeet | Completed
Milestone 2 | Milestone 2 | US-04 | As a user, I want a Relevance Agent to score how directly a response addresses the question, with reasoning. | Must | US-01, US-02 | Sumeet | Completed
Milestone 2 | Milestone 2 | US-05 | As a user, I want an Accuracy Agent to verify factual correctness using the reference answer or retrieved evidence. | Must | US-02 | Sumeet | Completed
Milestone 2 | Milestone 2 | US-06 | As a user, I want a Hallucination Detection Agent to flag unsupported or fabricated claims in a response. | Must | US-02, US-05 | Sumeet | Completed
Milestone 3 | Milestone 3 | US-07 | As a user, I want a Completeness Agent to identify aspects of the question that were left unanswered. | Must | Evaluation pipeline | Sumeet | Completed
Milestone 3 | Milestone 3 | US-08 | As a user, I want a Verdict Agent to combine the four dimension scores into a Pass, Needs Improvement, or Fail outcome using weighted scoring. | Must | US-04 to US-07 | Sumeet | Completed
Milestone 3 | Milestone 3 | US-09 | As a user, I want a results interface that shows per-dimension scores, reasoning, and the final verdict. | Must | US-04 to US-08 | Sumeet | Completed
Milestone 3 | Milestone 3 | US-10 | As a user, I want to upload a CSV of multiple question-response pairs and evaluate them in a single batch run. | Must | Evaluation pipeline | Sumeet | Completed
Milestone 4 | Milestone 4 | US-11 | As a user, I want a dashboard with filters and charts summarizing batch evaluation quality. | Must | US-10 | Sumeet | Completed
Milestone 4 | Milestone 4 | US-12 | As a user, I want to export batch evaluation results as a PDF report. | Must | US-10, US-11 | Sumeet | Completed
Milestone 4 | Milestone 4 | US-13 | As a developer, I want an automated test suite covering single and batch evaluation workflows end to end. | Must | All modules | Sumeet | Completed
Milestone 4 | Milestone 4 | US-14 | As a stakeholder, I want a project report and technical documentation describing the finished system. | Should | Completed system | Sumeet | Completed

## Sprint Backlog
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21 | Day 22 | Day 23 | Day 24 | Day 25 | Day 26 | Day 27 | Day 28 | Day 29 | Day 30 | Day 31 | Day 32 | Day 33 | Day 34 | Day 35 | Day 36 | Day 37 | Day 38 | Day 39 | Day 40 | Day 41 | Day 42 | Day 43 | Day 44 | Day 45 | Day 46 | Day 47 | Day 48 | Day 49 | Day 50 | Day 51 | Day 52
US-01 | M1-T01 | Research LLM evaluation methods, hallucination detection, and RAG techniques | 30-Jun-2026 | 02-Jul-2026 | Sumeet | Research | Completed | 6 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | M1-T02 | Design the multi-agent architecture, scoring dimensions, and data model | 01-Jul-2026 | 04-Jul-2026 | Sumeet | System Design | Completed | 8 | 0 | 1 | 2 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | M1-T03 | Build the evaluation input module for question, response, and optional reference answer | 03-Jul-2026 | 06-Jul-2026 | Sumeet | Implementation | Completed | 8 | 0 | 0 | 0 | 1 | 2 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | M1-T04 | Chunk reference datasets, generate embeddings, and build the ChromaDB retrieval index | 04-Jul-2026 | 08-Jul-2026 | Sumeet | RAG Development | Completed | 12 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | M1-T05 | Validate retrieval quality end-to-end and prepare Milestone 1 submission | 08-Jul-2026 | 09-Jul-2026 | Sumeet | Validation | Completed | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | M2-T01 | Implement the Relevance Agent | 10-Jul-2026 | 14-Jul-2026 | Sumeet | Agent Development | Completed | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-05 | M2-T02 | Implement the Accuracy Agent with supporting evidence lookup | 13-Jul-2026 | 17-Jul-2026 | Sumeet | Agent Development | Completed | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-06 | M2-T03 | Implement the Hallucination Detection Agent | 15-Jul-2026 | 19-Jul-2026 | Sumeet | Agent Development | Completed | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | M2-T04 | Validate the three judge agents against varied question-response pairs and prepare Milestone 2 submission | 18-Jul-2026 | 21-Jul-2026 | Sumeet | Validation | Completed | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-07 | M3-T01 | Implement the Completeness Agent | 22-Jul-2026 | 25-Jul-2026 | Sumeet | Agent Development | Completed | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-08 | M3-T02 | Implement the Verdict Agent with weighted score aggregation and quality gate | 24-Jul-2026 | 28-Jul-2026 | Sumeet | Agent Development | Completed | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-09 | M3-T03 | Build the per-dimension scoring and reasoning results interface | 26-Jul-2026 | 29-Jul-2026 | Sumeet | UI Development | Completed | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-10 | M3-T04 | Implement the CSV batch evaluation pipeline with aggregated results and prepare Milestone 3 submission | 27-Jul-2026 | 31-Jul-2026 | Sumeet | Batch Processing | Completed | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-11 | M4-T01 | Build the evaluation dashboard with multi-filter views and analytics charts | 01-Aug-2026 | 05-Aug-2026 | Sumeet | Dashboard | Completed | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-12 | M4-T02 | Implement SQLite-backed evaluation history and PDF report export | 04-Aug-2026 | 07-Aug-2026 | Sumeet | Report Generation | Completed | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-13 | M4-T03 | Build and run the automated test suite for single and batch evaluation workflows | 07-Aug-2026 | 11-Aug-2026 | Sumeet | Testing | Completed | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-14 | M4-T04 | Draft the technical documentation and project report | 09-Aug-2026 | 13-Aug-2026 | Sumeet | Documentation | Completed | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-14 | M4-T05 | Finalize documentation, agile artifacts, and demonstration readiness; prepare Milestone 4 submission | 14-Aug-2026 | 20-Aug-2026 | Sumeet | Finalization | Completed | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 1 | 2 | 2 | 3 | 0
Total | [7 empty] | 171 | 3 | 3 | 3 | 4 | 5 | 4 | 5 | 4 | 4 | 4 | 3 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 4 | 4 | 3 | 4 | 2 | 4 | 4 | 3 | 2 | 1 | 2 | 2 | 1 | 2 | 2 | 3 | 0

## Stand up Meeting
Sprint / Milestone | Date | Impediment / Discussion | Action Taken
Milestone 1 | 02-Jul-2026 | Needed to lock down the overall system design before writing code. | Finalized the multi-agent architecture, scoring dimensions, and data model.
Milestone 1 | 05-Jul-2026 | RAG knowledge base was built but not yet connected to the live evaluation flow. | Traced the evaluation pipeline end-to-end and wired retrieval into the live agent calls instead of assuming it was already connected.
Milestone 1 | 08-Jul-2026 | st.progress() crashed when passed a negative cosine similarity value during a retrieval preview. | Clamped similarity scores to a valid range before passing them to the progress bar.
Milestone 1 | 09-Jul-2026 | Milestone 1 submission required a final end-to-end validation of retrieval. | Validated and finalized the RAG pipeline ahead of submission.
Milestone 2 | 12-Jul-2026 | Relevance Agent output needed to be integrated into the orchestrator. | Wired the Relevance Agent into the main evaluation flow.
Milestone 2 | 15-Jul-2026 | Hallucination Detection Agent was mislabeling true claims as hallucinated when no reference answer was supplied. | Added an explicit 'verifiable' flag threaded through the agent output so unverifiable-but-true claims aren't penalized as hallucinations.
Milestone 2 | 18-Jul-2026 | Accuracy Agent needed grounded evidence when no reference answer was available. | Connected retrieved RAG evidence as a fallback grounding source for accuracy checks.
Milestone 2 | 21-Jul-2026 | Milestone 2 submission required validation across varied QA pairs. | Tested all three judge agents on varied inputs and prepared the submission.
Milestone 3 | 24-Jul-2026 | Started implementation of the Completeness Agent. | Implemented completeness scoring against the identified sub-questions.
Milestone 3 | 26-Jul-2026 | Verdict Agent scores did not match the score rings on the results interface; rings showed zero regardless of the actual scores. | Traced the issue to a silent field-name mismatch between the Verdict Agent output and the frontend schema; aligned field names across agents, the Verdict Agent, and the UI.
Milestone 3 | 29-Jul-2026 | Needed a clear way to present per-dimension scores and reasoning to the user. | Built the results interface showing per-dimension scores, reasoning, and final verdict.
Milestone 3 | 31-Jul-2026 | Milestone 3 submission required the batch CSV pipeline to be validated. | Built and validated the batch CSV evaluation pipeline ahead of submission.
Milestone 4 | 03-Aug-2026 | Dashboard cards built using card_open()/card_close() st.markdown() calls weren't actually wrapping the widgets inside them. | Replaced the pattern with st.container(key=...) as a context manager and targeted the generated st-key- CSS classes for styling.
Milestone 4 | 05-Aug-2026 | Side-by-side system comparison on the dashboard became unreadable when too many systems were selected. | Capped the comparison view to 4 columns and added a multiselect picker to choose which systems to compare.
Milestone 4 | 07-Aug-2026 | PDF export was silently missing RAG-related warnings that should have appeared for ungrounded responses. | Traced the issue to _normalize_all() dropping the 'rag' key during normalization; fixed the function to preserve it.
Milestone 4 | 11-Aug-2026 | Pytest fixture data (e.g. IntegrationTestSystem records) was being written into the real evaluation_history.db, corrupting the live dashboard. | Made DB_PATH overridable via an environment variable and isolated test state in conftest.py using a temporary database file.
Milestone 4 | 14-Aug-2026 | Needed to review and polish the written deliverables before submission. | Reviewed and refined the technical documentation, project report, and Agile documentation.
Milestone 4 | 20-Aug-2026 | Final review before submission. | Completed final review and assembled the submission package.

## Retrospection
Milestone | Team Member | What Went Well (Continue Doing) | What Didn't Go Well (Stop Doing) | What To Improve (Start Doing) | Action Taken
Milestone 1 | Sumeet | Kept the modular agent design and RAG grounding central to the architecture from the start. | Assumed the RAG pipeline was wired into evaluation just because it existed; also assumed similarity scores would never be negative. | Verify end-to-end wiring explicitly instead of assuming a built component is connected; validate numeric ranges before feeding them to UI widgets. | Traced and fixed the RAG wiring gap; clamped similarity scores before display.
Milestone 2 | Sumeet | Kept agent reasoning explicit and explainable across Relevance, Accuracy, and Hallucination agents. | Treated unverifiable claims the same as false claims when no reference answer was available. | Thread explicit flags (like 'verifiable') through agent outputs whenever reference data may be missing. | Added a 'verifiable' flag across agents, the Verdict Agent, and PDF export.
Milestone 3 | Sumeet | Kept dimension scores and the final verdict cleanly separated in the scoring model. | Assumed a zero score on the UI meant a genuinely failing evaluation, rather than checking for a data issue. | Actively check schema alignment between agents, the Verdict Agent, and the frontend after every change. | Fixed the field-name mismatch causing score rings to zero out and added integration checks.
Milestone 4 | Sumeet | Kept the dashboard, PDF reporting, and test suite aligned with the core evaluation pipeline. | Reused a Streamlit card pattern that didn't actually wrap widgets; let test fixtures write into the production database by default. | Isolate test data from production from day one; verify UI container patterns actually behave as intended before building on top of them. | Made DB_PATH overridable and isolated test state in conftest.py; switched to st.container(key=...) for cards; capped dashboard comparison columns; fixed _normalize_all() dropping the 'rag' key.

## Defect Tracker
Sl No | Submitted By | Submitted Date | Description | Detected Milestone | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status (Open/Closed) | Remarks
1 | Sumeet | 08-Jul-2026 | RAG knowledge base was built but never wired into the live evaluation flow. | Milestone 1 | Sumeet | Integration | Traced the evaluation pipeline end-to-end and connected retrieval calls to the live agent flow instead of assuming the wiring was already in place. | 09-Jul-2026 | Closed | Verified by re-running Milestone 1 validation.
2 | Sumeet | 08-Jul-2026 | st.progress() crashed when passed a negative cosine similarity value during a retrieval preview. | Milestone 1 | Sumeet | UI / Robustness | Clamped similarity scores to a valid 0-1 range before passing them to the progress bar. | 09-Jul-2026 | Closed | No further crashes observed in retrieval preview.
3 | Sumeet | 16-Jul-2026 | Hallucination Detection Agent mislabeled true claims as hallucinated when no reference answer was supplied. | Milestone 2 | Sumeet | Logical | Added an explicit 'verifiable' flag threaded through the agent output, Verdict Agent, and PDF export so unverifiable-but-true claims are not penalized as hallucinations. | 17-Jul-2026 | Closed | Confirmed correct handling on QA pairs without reference answers.
4 | Sumeet | 26-Jul-2026 | Verdict Agent scores did not match the score rings on the results interface; rings showed zero regardless of actual scores. | Milestone 3 | Sumeet | Integration | Found a silent field-name mismatch between Verdict Agent output keys and the frontend schema; aligned field names across agents, the Verdict Agent, and the UI. | 27-Jul-2026 | Closed | Score rings now render correctly across all dimensions.
5 | Sumeet | 03-Aug-2026 | Dashboard cards built with card_open()/card_close() st.markdown() calls did not actually wrap the widgets inside them. | Milestone 4 | Sumeet | UI | Replaced the pattern with st.container(key=...) as a context manager and targeted the generated st-key- CSS classes for styling. | 03-Aug-2026 | Closed | Cards now render with widgets correctly contained.
6 | Sumeet | 05-Aug-2026 | Side-by-side system comparison on the dashboard became unreadable when too many systems were selected at once. | Milestone 4 | Sumeet | UI / UX | Capped the comparison view to 4 columns and added a multiselect picker to choose which systems to compare. | 05-Aug-2026 | Closed | Layout stays readable regardless of how many systems exist.
7 | Sumeet | 07-Aug-2026 | PDF report export was silently missing RAG-related warnings that should have appeared for ungrounded responses. | Milestone 4 | Sumeet | Data Integrity | Traced the issue to _normalize_all() dropping the 'rag' key during normalization; fixed the function to preserve it. | 07-Aug-2026 | Closed | Warnings now appear correctly in both the dashboard and the exported PDF.
8 | Sumeet | 11-Aug-2026 | Pytest fixture data (e.g. IntegrationTestSystem records) was being written into the real evaluation_history.db, corrupting the live dashboard. | Milestone 4 | Sumeet | Test Isolation | Made DB_PATH overridable via an environment variable and isolated test state in conftest.py using a temporary database file. | 11-Aug-2026 | Closed | Production dashboard no longer shows test data; full pytest suite passes against an isolated DB.

## Unit Test Plan
Test ID | Module / Agent | Test Description | Test Type | Expected Result | Actual Result
UT-01 | Evaluation Input Module | Verify a question, response, and optional reference answer are accepted and validated correctly. | Unit | Input is validated and stored in the expected schema. | Passed
UT-02 | RAG Knowledge Base | Verify documents are chunked, embedded, and indexed into ChromaDB correctly. | Unit | Chunks are embedded and retrievable by similarity search. | Passed
UT-03 | RAG Retrieval | Verify retrieval returns the most relevant chunks for a given query, including edge cases with negative similarity. | Unit | Relevant chunks returned; similarity values clamped to a valid range. | Passed
UT-04 | Relevance Agent | Verify the agent scores how directly a response addresses the question, with reasoning. | Unit | Score and reasoning returned in the expected schema. | Passed
UT-05 | Accuracy Agent | Verify the agent checks factual correctness against a reference answer or retrieved evidence. | Unit | Correct accuracy score and supporting evidence returned. | Passed
UT-06 | Hallucination Detection Agent | Verify unsupported claims are flagged, and unverifiable-but-true claims are not penalized. | Unit | Hallucinated claims flagged; verifiable flag correctly applied. | Passed
UT-07 | Completeness Agent | Verify unanswered aspects of the question are correctly identified. | Unit | Missing sub-questions correctly identified. | Passed
UT-08 | Verdict Agent | Verify the four dimension scores are combined into a weighted final verdict with the quality gate applied. | Unit | Correct Pass / Needs Improvement / Fail verdict returned. | Passed
UT-09 | Verdict Agent - Field Schema | Verify Verdict Agent output field names match the frontend schema exactly. | Regression | Score rings render correctly, no zeroed-out scores. | Passed
UT-10 | Batch CSV Pipeline | Verify a CSV of multiple question-response pairs is evaluated correctly in a single batch run. | Integration | All rows evaluated and aggregated results returned. | Passed
UT-11 | Dashboard Filters | Verify multi-filter views on the dashboard return the correct subset of evaluation history. | Integration | Filtered results match applied filter criteria. | Passed
UT-12 | Dashboard Comparison View | Verify the system comparison view stays readable when more than 4 systems exist. | UI | Comparison capped at 4 columns with a multiselect picker. | Passed
UT-13 | PDF Export | Verify PDF reports are generated correctly, including RAG-related warnings for ungrounded responses. | Integration | PDF generated with correct scores, verdicts, and warnings. | Passed
UT-14 | SQLite Evaluation History | Verify evaluation results are persisted correctly to evaluation_history.db. | Integration | Records persisted and retrievable via the dashboard. | Passed
UT-15 | Test / Production DB Isolation | Verify pytest fixture data never writes into the production evaluation_history.db. | Regression | Test runs use an isolated temp DB via overridable DB_PATH. | Passed
UT-16 | End-to-End Workflow | Verify a full single evaluation and a full batch evaluation run end-to-end without errors. | End-to-End | Both workflows complete and produce correct final verdicts. | Passed